## Sheet1
Role | Action Item | Deliverable | Target Completion | Status
CTO | Implement Redis sharding and load management | Reduce memory usage spikes and improve high-load performance | March 29, 2025 | In Progress
COO | Complete Redis scaling strategy | Ensure infrastructure is prepared for 2x traffic volume | March 29, 2025 | In Progress
CMO | Launch LinkedIn and email outreach campaigns | Increase brand awareness and lead generation | April 10, 2025 | Planned
CFO | Update budget forecast based on Redis sharding and AI model costs | Ensure financial readiness for infrastructure scaling | April 1, 2025 | In Progress
CSO | Define outreach strategy for finance and healthcare sectors | Target high-value enterprise clients in regulated sectors | April 12, 2025 | In Progress
CPO | Improve AI command interface feedback loop | Enhance user experience and AI-generated content feedback | April 5, 2025 | In Progress
CAIO | Improve AI response consistency and handling of complex commands | Increase AI output accuracy for multi-step commands | April 5, 2025 | In Progress
CISO | Improve logging frequency and depth for AI-generated content | Improve compliance visibility and content filtering accuracy | April 5, 2025 | In Progress